[image: image1.jpg]B | mrcarpet

. DESIGNS FOR FLOORS





70 Lower Richmond Road

Putney, London

SW15 1LL

Tel Nr:
020-8789-3133

Fax Nr:
020-8780-2140

	Mr Suresh Kerai

	Vascroft Contractors Ltd

	861 Coronation Road

	Park Royal, London

	NW10 7PT


22nd July 2013
Dear Suresh,
Re: “Blue Jay”, 16 Claremont Drive, Esher, KT10 9LU

Queries following my site visit & meeting with ‘Khimji’ on Thursday 18th July:-
1) Site not ready for carpet installation to commence on Monday 22nd July as previously requested. As this is the 2nd postponement (installation originally requested to commence on 15th July), please advise firm dates ASAP when each area will be ready to receive carpeting? Khimji said it would be OK to install the Master Bedroom & Dressing room carpets this week, (subject to the dressing room cupboards being completed) so we have scheduled these areas to be fitted on Wed 24th & Thurs 25th July. Please confirm urgently this is still OK?
2) We only discovered on Thursday that under floor heating is installed throughout the property. The 42oz Felt underlay allowed for in our quote is not suitable for use over under floor heating as it will not allow enough heat to travel through it, therefore we recommend upgrading to a special “Low Tog” rubber underlay that is specifically designed for use over under floor heating. The additional cost would be as follows:-
Master Bedroom / Dressing Rooms 1 & 2 / Drum Landing & Entertainment room

Supply Low Tog (0.80 tog) rubber underlay
  £2,087.15
Less cost allowed for 42oz Felt underlay
- £1,328.23
Additional cost variation to be added to the original order 
+ £759.02 + Vat
3) Due to the concrete construction of the Main stairs we recommend using a heavier duty Felt / Crumb Rubber combination underlay called ‘Luxifelt’ rather than the 42oz felt allowed for in our quote. This will help protect the carpet from premature wear caused by damage from the right angled concrete step edges, (which are quite sharp in places). The additional cost would be as follows:-

Main Stairs (drum landing to ground floor)
Supply Luxifelt Crumb Rubber / Felt combination underlay  
  £107.40
Less cost allowed for 42oz Felt underlay
- £63.00
Additional cost variation to be added to the original order 
+ £44.40 + Vat
All prices exclude VAT @ 20%

[image: image2.jpg]B | mrcarpet

. DESIGNS FOR FLOORS





70 Lower Richmond Road

Putney, London

SW15 1LL

Tel Nr:
020-8789-3133

Fax Nr:
020-8780-2140

	Mr Suresh Kerai

	Vascroft Contractors Ltd

	861 Coronation Road

	Park Royal, London

	NW10 7PT


22nd July 2013
4) During our site visit last Thursday we discovered the stairs between the ground floor & basement (before that time we had no knowledge of this staircase). Please confirm if this staircase is to be carpeted using the same carpet specified for the back stairs between the ground & 1st floor? If so, the additional cost would be as follows:-

Stairs from Ground Floor to Basement
Supply New Worlds “Argentina”, 100% Wool carpeting, 4 metre wide, @ £23.81m² + VAT
42oz Felt underlay to be laid beneath,

Fitting to same by gripperods installation,

Normal Retail Price                          

 £ 604.42
Less Trade Discount                        

-£ 36.04
Discount Price                                 

 £568.38 + Vat
5) Please confirm if you would like us to supply & fit Polished Chrome doorbars at the following doorways. 

DF12 – Bed 2

DF05 – Bed 3

DF07 – Bed 4

DF09 – Bed 5

DF11 - Services Cupboard

DF20 – Den

If so the additional cost would be £37.50 + Vat per doorway.

If you would like us to supply these extra doorbars please specify what type of flooring is to be installed (by others) in each of the areas listed
All prices exclude VAT @ 20%

[image: image3.jpg]B | mrcarpet

. DESIGNS FOR FLOORS





70 Lower Richmond Road

Putney, London

SW15 1LL

Tel Nr:
020-8789-3133

Fax Nr:
020-8780-2140

	Mr Suresh Kerai

	Vascroft Contractors Ltd

	861 Coronation Road

	Park Royal, London

	NW10 7PT


22nd July 2013
6) We are unable to see from current site conditions how the carpet can be best fitted between the upper & lower sections of the entertainment room or to the 2 sets of steps between the upper & lower areas in this room, therefore please provide drawings showing details of the proposed edge finish detail relating to these areas.

7) Please confirm that there will be 240v power available on site at the time of installation as this will be required for the fitters heat seam irons which are used to join the sections of carpet together
8) It was noted during our survey that the areas to be carpet are still very dusty. We would strongly recommend that all areas to be carpeted are thoroughly cleaned prior to the arrival of the carpets to minimize the chance of the dust marking the carpets
9) Please confirm that the 2nd payment (as per our Pro-Forma invoiced dated 10th July 2013) has been sent as this is required prior to commencement of installation as per the terms agreed with my MD.
I look forward to receiving your reply in due course
Yours sincerely
Nigel Symonds

All prices exclude VAT @ 20%
This document was produced electronically and is valid without a signature.


